## Dashboard
PROJECT TRACKING |  |  |  | 17-02-20 to 13-03-20
Project | Task | Manager | Start Date | Days completed | End Date | Progress | Duration | Budget | Actual | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13
Alpha | Task 1 | Andy | 4388900% | 3 | 4390000% | 37.5% | 8 | 96000 | 32256
| Task 2 | Obi | 4389200% | 4 | 4390200% | 44.44% | 9 | 513000 | 226233
| Task 3 | Oluchi | 4388100% | 3 | 4388700% | 60% | 5 | 616000 | 401579
| Task 4 | Ifeoma | 4388000% | 3 | 4388200% | 100% | 3 | 817000 | 807069
| Task 5 | Christabel | 4388200% | 3 | 4389200% | 42.86% | 7 | 372000 | 173166
| Task 6 | Andy | 4388500% | 2 | 4389600% | 20% | 10 | 50000 | 8400
| Task 7 | Obi | 4388500% | 3 | 4389600% | 30% | 10 | 807000 | 262679
| Task 8 | Oluchi | 4388500% | 0 | 4388700% | 0% | 3 | 691000 | 0
Delta | Task 1 | Ifeoma | 4389200% | 8 | 4390200% | 88.89% | 9 | 787000 | 727188
| Task 2 | Christabel | 4389200% | 2 | 4390300% | 20% | 10 | 228000 | 47880
| Task 3 | Andy | 4387800% | 0 | 4388100% | 0% | 4 | 147000 | 0
| Task 4 | Obi | 4388000% | 5 | 4388900% | 62.5% | 8 | 338000 | 205123
| Task 5 | Oluchi | 4388500% | 3 | 4389600% | 30% | 10 | 857000 | 305949
| Task 6 | Ifeoma | 4388600% | 3 | 4389300% | 50% | 6 | 602000 | 322371
| Task 7 | Christabel | 4388600% | 2 | 4388900% | 50% | 4 | 990000 | 451440
Gemini | Task 1 | Ifeoma | 4387800% | 2 | 4388200% | 40% | 5 | 218000 | 97337
| Task 10 | Oluchi | 4388500% | 3 | 4389200% | 50% | 6 | 416000 | 175015
| Task 2 | Christabel | 4387800% | 3 | 4388500% | 50% | 6 | 393000 | 177440
| Task 3 | Andy | 4387900% | 4 | 4389200% | 40% | 10 | 86000 | 31046
| Task 4 | Obi | 4388200% | 3 | 4389400% | 33.33% | 9 | 732000 | 261324
| Task 5 | Oluchi | 4387800% | 1 | 4388100% | 25% | 4 | 492000 | 116850
| Task 6 | Ifeoma | 4388100% | 0 | 4388800% | 0% | 6 | 188000 | 0
| Task 7 | Christabel | 4388100% | 3 | 4388900% | 42.86% | 7 | 180000 | 79380
| Task 8 | Andy | 4388500% | 2 | 4388900% | 40% | 5 | 582000 | 195231
| Task 9 | Obi | 4388500% | 1 | 4389500% | 11.11% | 9 | 562000 | 74746
Orion | Task 1 | Ifeoma | 4387900% | 7 | 4388700% | 100% | 7 | 293000 | 273001
| Task 10 | Oluchi | 4387800% | 3 | 4388000% | 100% | 3 | 68000 | 64987
| Task 2 | Christabel | 4387800% | 4 | 4388800% | 44.44% | 9 | 224000 | 57910
| Task 3 | Andy | 4387900% | 0 | 4388800% | 0% | 8 | 978000 | 0
| Task 4 | Obi | 4388100% | 3 | 4388900% | 42.86% | 7 | 932000 | 379157
| Task 5 | Oluchi | 4388200% | 1 | 4388700% | 25% | 4 | 854000 | 322812
| Task 6 | Ifeoma | 4388200% | 3 | 4388900% | 50% | 6 | 81000 | 38461
| Task 7 | Christabel | 4388500% | 5 | 4389200% | 83.33% | 6 | 169000 | 136468
| Task 8 | Andy | 4388600% | 1 | 4388900% | 25% | 4 | 61000 | 12078
| Task 9 | Obi | 4388800% | 3 | 4389600% | 42.86% | 7 | 645000 | 273048
Vega | Task 1 | Ifeoma | 4387800% | 5 | 4388900% | 50% | 10 | 839000 | 406974
| Task 2 | Christabel | 4388200% | 4 | 4388800% | 80% | 5 | 729000 | 487139
| Task 3 | Andy | 4388500% | 3 | 4389300% | 42.86% | 7 | 826000 | 298186
| Task 4 | Obi | 4388700% | 2 | 4389500% | 28.57% | 7 | 895000 | 280583
| Task 5 | Oluchi | 4388900% | 2 | 4389300% | 66.67% | 3 | 341000 | 129785
Grand Total | [7 empty] | 19695000 | 8340291
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Data
Project | Task | Manager | Start Date | Duration | End Date | Days completed | Progress | Budget | Actual
Gemini | Task 1 | Ifeoma | 4387800% | 5 | 4388200% | 2 | 40% | 218000 | 97337
Orion | Task 1 | Ifeoma | 4387900% | 7 | 4388700% | 7 | 100% | 293000 | 273001
Vega | Task 1 | Ifeoma | 4387800% | 10 | 4388900% | 5 | 50% | 839000 | 406974
Delta | Task 1 | Ifeoma | 4389200% | 9 | 4390200% | 8 | 88.89% | 787000 | 727188
Alpha | Task 1 | Andy | 4388900% | 8 | 4390000% | 3 | 37.5% | 96000 | 32256
Gemini | Task 10 | Oluchi | 4388500% | 6 | 4389200% | 3 | 50% | 416000 | 175015
Orion | Task 10 | Oluchi | 4387800% | 3 | 4388000% | 3 | 100% | 68000 | 64987
Gemini | Task 2 | Christabel | 4387800% | 6 | 4388500% | 3 | 50% | 393000 | 177440
Orion | Task 2 | Christabel | 4387800% | 9 | 4388800% | 4 | 44.44% | 224000 | 57910
Vega | Task 2 | Christabel | 4388200% | 5 | 4388800% | 4 | 80% | 729000 | 487139
Delta | Task 2 | Christabel | 4389200% | 10 | 4390300% | 2 | 20% | 228000 | 47880
Alpha | Task 2 | Obi | 4389200% | 9 | 4390200% | 4 | 44.44% | 513000 | 226233
Alpha | Task 3 | Oluchi | 4388100% | 5 | 4388700% | 3 | 60% | 616000 | 401579
Gemini | Task 3 | Andy | 4387900% | 10 | 4389200% | 4 | 40% | 86000 | 31046
Orion | Task 3 | Andy | 4387900% | 8 | 4388800% | 0 | 0% | 978000 | 0
Vega | Task 3 | Andy | 4388500% | 7 | 4389300% | 3 | 42.86% | 826000 | 298186
Delta | Task 3 | Andy | 4387800% | 4 | 4388100% | 0 | 0% | 147000 | 0
Alpha | Task 4 | Ifeoma | 4388000% | 3 | 4388200% | 3 | 100% | 817000 | 807069
Gemini | Task 4 | Obi | 4388200% | 9 | 4389400% | 3 | 33.33% | 732000 | 261324
Orion | Task 4 | Obi | 4388100% | 7 | 4388900% | 3 | 42.86% | 932000 | 379157
Vega | Task 4 | Obi | 4388700% | 7 | 4389500% | 2 | 28.57% | 895000 | 280583
Delta | Task 4 | Obi | 4388000% | 8 | 4388900% | 5 | 62.5% | 338000 | 205123
Gemini | Task 5 | Oluchi | 4387800% | 4 | 4388100% | 1 | 25% | 492000 | 116850
Orion | Task 5 | Oluchi | 4388200% | 4 | 4388700% | 1 | 25% | 854000 | 322812
Vega | Task 5 | Oluchi | 4388900% | 3 | 4389300% | 2 | 66.67% | 341000 | 129785
Delta | Task 5 | Oluchi | 4388500% | 10 | 4389600% | 3 | 30% | 857000 | 305949
Alpha | Task 5 | Christabel | 4388200% | 7 | 4389200% | 3 | 42.86% | 372000 | 173166
Gemini | Task 6 | Ifeoma | 4388100% | 6 | 4388800% | 0 | 0% | 188000 | 0
Orion | Task 6 | Ifeoma | 4388200% | 6 | 4388900% | 3 | 50% | 81000 | 38461
Delta | Task 6 | Ifeoma | 4388600% | 6 | 4389300% | 3 | 50% | 602000 | 322371
Alpha | Task 6 | Andy | 4388500% | 10 | 4389600% | 2 | 20% | 50000 | 8400
Gemini | Task 7 | Christabel | 4388100% | 7 | 4388900% | 3 | 42.86% | 180000 | 79380
Orion | Task 7 | Christabel | 4388500% | 6 | 4389200% | 5 | 83.33% | 169000 | 136468
Delta | Task 7 | Christabel | 4388600% | 4 | 4388900% | 2 | 50% | 990000 | 451440
Alpha | Task 7 | Obi | 4388500% | 10 | 4389600% | 3 | 30% | 807000 | 262679
Alpha | Task 8 | Oluchi | 4388500% | 3 | 4388700% | 0 | 0% | 691000 | 0
Gemini | Task 8 | Andy | 4388500% | 5 | 4388900% | 2 | 40% | 582000 | 195231
Orion | Task 8 | Andy | 4388600% | 4 | 4388900% | 1 | 25% | 61000 | 12078
Gemini | Task 9 | Obi | 4388500% | 9 | 4389500% | 1 | 11.11% | 562000 | 74746
Orion | Task 9 | Obi | 4388800% | 7 | 4389600% | 3 | 42.86% | 645000 | 273048
Formulas:
End Date = WORKDAY.INTL([Start Date]-1,[Duration],1)

## Workings
Not Started | 4 | Values |  |  | Doughnut |  | Actual | Budget | Scroll Bar
In Progress | 33 | Sum of Days completed | 112 | Days Closed Out | 42.11% | Bar Chart | 8340291 | 19695000 | 0
Completed | 3 | Sum of Duration | 266 | Days Outstanding | 57.89% | Doughnut | 42.35% | 57.65%
Outstanding | 37
Total Task | 40